# Alwoodley Parish Council Action Plan (Draft)

# 2026/2027 – October 2026 Update

This document sets out the various actions to be undertaken by the Alwoodley Parish Council in 2026/2027 .

Managing risk: The majority of projects included on the Action Plan for 26/27 have budget provision in place and do not require external funding.

Delivery timeframe: Committees/ Project Leads will set their own timeframes for milestones in project delivery. All actions to be completed within the financial year 2025/26, unless stated/ongoing. A mid-year review will be carried out in November 2026.

|  | Priority Statement(s) for 2026/2027 | Actions Agreed for 2026/2027 | By whom | By When | Status as of August 25th 2026 |
| --- | --- | --- | --- | --- | --- |
| Finance | To strengthen financial resilience and mitigate risk by implementing systems created in 2026/2027 year. | - Transfer reserve funds to Virgin & Close Lloyds bank account - Set up reserves account in Virgin - Ensure adequate number of signatories. - Ensure Schedule of Payments is reviewed and signed ahead of full council meetings - Implement monthly financial oversight rota | - Cllr Townes - Clerk and Cllr Towns - “” - Clerk, Cllr Wright, Cllr Downes, Cllr Jordan, Cllr Towns - Whole council & Clerk | - 31 May 2026 - 31 July 2026 - “” - Immediately, monthly - Immediately, monthly | - Signatories updated and adequate number. They can now set up deposit account at Virgin and transfer funds.Geoff to prepare closure form for Lloyds for October meeting. - Not yet completed - Complete for virgin. Need to get Cllr Jordan and Wright back online for approvals. - System is now established and running regularly. - Monthly financial oversight rota is now up and running. |
| Governance & Transparency & Planning | To move from Bronze to Silver level of Governance and Transparency. | - Apply for bronze award - Develop tracker of progress towards silver award. - Update full council on progress at each meeting | - Clerk - Clerk - Clerk | - May 31st 2026 - August 30th 2026 - 3. Ongoing | - Clerk submitted application on 15 June. Invoice for application fee included in schedule of payments. ** October Update; Clerk has received triage feedback and requires a review and confirmation by council that the revised application is ready for submission at the October meeting. - Deferred until 2027/2028 as Bronze application has taken longer than expected. - Ongoing |
| Learning, Development and Capacity Building | To develop and a plan based on needs assessment of each councillor and their committee work. | Individual Councillors to submit needs assessment | Each Councillor | 30th April | Inventory as of October 2026 Training Plan https://www.alwoodleyparishcouncil.gov.uk/document/training-plan-for-2026-2027-approved-june-2026/ |
|  |  | Clerk to compile needs assessments and draft plan for review and approval | Clerk | 11th May | Complete |
|  |  | Council to review, amend and approve training plan. | Full Council | 11th May | Complete Training Plan https://www.alwoodleyparishcouncil.gov.uk/document/training-plan-for-2026-2027-approved-june-2026/ |
|  |  | Clerk to order books and Councillors to book themselves into training according to the plan. Clerk to book any whole council training determined by plan | Per assigned in training and development plan. | By June meeting and ongoing as training sessions become available. | In progress. Whole council training deferred until two new councillors co-opted. |
|  | 100% of Councillors and staff undergo training. | Councillors and Staff to undergo training per approved plan | Each Councillor and Clerk | 31 March 2026 | On track |
| Community Engagement, Participation and Democracy | Priority #1 To build trust with the community by delivering highly visible events and festive enhancements that bring people together. | 1. Organise 2 Band Concerts/ Community Picnics together with brass bands organised by Leeds City Council, which includes booking two bands, arranging chairs, and promoting the event. 2. Deliver a Winter event, ensuring robust outreach, poster campaigns, and an attraction such as Santa. - Expand the festive lighting to include an instalment that creates a focal point and a reason to gather (e.g. alternative to a tree-lighting that is multi-cultural such as a community art project that schools and groups contribute to that can be lit up)* I know an artist who has organised lantern festivals and these kind of instalments that we could reach out to for a quote. - Host an interactive Annual Parish Meeting, providing refreshments, active promotion, and potentially a guest speaker to encourage resident attendance. |  |  | - 21st June Band Concert and Community Pincic complete. September band cncert complete. - Plans for event tbd. - Clerk received prices from Leeds City council and sent to working Party. Working Party recommended removal of tree lights, maintaining motifs this was approved by council. Clerk communicated this to LCC and obtained quote. Engagement committee reaching out to business owners including Café Espressio and Café 17 re Christmas tree by Café Espresso and lights on existing fir tree. (café 17). Require update on community engagement/multicultural elements. - Highly attended with guest speaker, TPO officer. complete. |
|  | Priority #2: To proactively communicate the benefits of the Parish Council to residents and actively engage them in planning for Alwoodley’s future by inviting ideas, participation in working groups, and joining the council. | 1. Publish and distribute two community newsletters over the course of the year. 2. Try out 2-3 pop up surgeries in various locations. 3. Develop flyers and signage inviting feedback and ideas via QR code and other creative methods. 4. Grow the Council's direct digital outreach to hit a target of 500 mailing list subscribers, utilising the Council's MailerLight subscription. 5.Develop and implement a communications plan to recruit new councillors 6. Coordinate with Planning Committee and Environment & biodiversity working party to engage to start collecting community ideas for the neighbourhood plan biodiversity plans | 1. Cllr Dickinson, Cllr Wright with input of all members and approval of full council. 2. Coordinated by working group, all members to participate in at least one. 3. TBD + Clerk 4. TBD + Clerk 5. TBD + Clerk 6. TBD + Clerk | 1. . [date] & [date] 2. [target dates/venues] 3. Ongoing. Numbers target by 31 March 2027. 4. January 30th 2027 5. June 30th 2026 6. June 30th 2026 | 1. Spring Summer Newsletter distributed. 2. Surgery dates to be approved at October meeting 3. Leeds Becket village green consultation will have engagement marquee and has flyer with QR code. Recent band concert engagement – councillors circulated with mailing list sign up sheet and asked for ideas about the parish. 4. List has grown from 67 in February to 87 in June to 102 on 26th August to 145 in October, due to Hedgehog Highways drive and band concert signups. . 5. No plan created yet, however, two new candidates coming forward to be co-opted in September and November 6. To be done after neighbourhood planning session with LCC |
|  | Priority #3 To fund a diverse range of local community organisations as a core part of the Council's visibility and engagement effort. | 1. Attend community meetings to get to know local orgs and their issues. Invite them to apply for grants proactively. 2. Award community grants to a variety of organisations that connect with a wide cross-section of parishioners. 3. Utilise Section 137 (S137) funding to support targeted local needs that fall outside standard grant powers, such as health services, adult social care, charity staffing, youth clubs, or dementia services. |  |  | - New liaison system established - 4 grants given to date (Maecare, Repair café, leeds rhinos and table tennis Assoc) - Maecare grant and Rhinos falls within S137 |
| Planning £15,000 earmarked reserve for neighbourhood planning process. | Priority 1- Prepare for expiration of Neighbourhood plan in 2028 and develop plan to review/update it. | - Enquire with LCC about process for reviewing the Parish Boundary and updating the Neighbourhood Plan - Arrange meeting /presentation to full council re 1. - Create timeline for moving forward with above based on advice which will involve community engagement, possible petition management for boundary change, research, meetings, and drafting of policy updates. - Improve habit of commenting on plans using neighbourhood plan. | - Clerk - “ | - May 2026 - September 2026 | - Prep meeting with LCC complete. Setting up whole council meeting with that office in October. - Oct 15th Date set. - Deferred until after Oct 15th Meeting - Clerk created reviewing checklist for use by committee members so that comments can refer to neighbourhood plan. |
|  | Priority 2 – Improve stewardship of neighborhood plan | - Undergo training on their duties - Review the neighbourhood plan and key elements to look out for in planning applications | - All planning committee members - All planning committee members, supported by Clerk | - By end of 2026 - By June meeting | - Meeting Scheduled with Ian MacKay form LCC to review / assess current plan |
| Environment, Biodiversity and Sustainability | Priority Statement: To lay the groundwork for a Local Nature Recovery Plan that integrates seamlessly with the West Yorkshire Local Nature Recovery Strategy (WYLNRS) and embeds biodiversity into the 2028 Neighbourhood Plan update | 1. Recommend updates to the Neibhourhood Plan in alignment with West Yorkshire Combined Authority's Local Nature Recovery Strategy ahead of it’s 2028 review. A) Investigate hiring an ecologist to review the current Alwoodley Parish neighbourhood plan and B) recommend to the full council updates that would embed nature recovery and sustainability priorities in the neighbourhood plan and other parish policies and projects 2. Meet with key partners (Yorkshire Water, WYCA, Leeds City Council, Large, Land owners) to collaborate on plan based on ecologists recommendations. 3. Liaise with LCC of the Parish Council's plans to fund and expand biodiversity & sustainability projects and seek necessary approvals/legal arrangements for community-led initiatives on their land. 4. Partner with local orgs to seek grant funding and deliver nature recovery plan. | - (a) Clerk to develop request for proposals for review by full council. (a2) provide three quotes to full council. (b) - Environment committee & Clerk/Planning Committee/Clerk - Clerk and working party - In collab with outreach working group | - (a1)Ahead of July meeting (a2) ahead of September or October meeting (depending on how swiftly the RFP is approved - By 31 march 2027 - By may 2027 - Throughout 2027/2028 | - The working party agreed that the actions associated with this statement would be revisited once the planned training on the Neighbourhood Plan had been received by the working party members. |
|  | Priority 1: Adopting Nature Corridors and Empowering the Parish Ranger To establish the Parish's foundational habitat network across the Meadow, Woodland, and Pond corridors by collaborating with the community to identify intervention sites and working with LCC to implement nature-friendly land management. | - Investigate a specific Parish initiative (Project) such as improving hedgehog numbers by involving the community in creating hedgehog friendly gardens, hedgehog highways and road signage in vulnerable areas. - Adopt the proposed nature corridors detailed in the "Enhancing Biodiversity" report and officially designate these corridors within the Parish. - Engage the community to Identify no-spraying, tree protection, and no-mow zones and propose to Leeds City Council. - Identify tasks for the Parish Ranger and / or other contractor to help manage these LCC-Agreed zones by creating wildlife-friendly fencing, educational signage, inviting displays to communicate nature-friendly management to the public. - Collaborate with partners who work in areas outside the Parish Boundaries | - Environmental Working Party - A) Clerk Invite author to speak at September meeting (Cerk) b) consider adoption at that meeting - Environmental Working Party - Environmental Working Party - Environmental Working Party* *lead to be named on each item asap | - June 1st - September 30th - Plan developed in October; for implementation throughout the following spring/summer - Beginning asap, integrate into regular council meeting. | Priority 1: Adopting Nature Corridors and Empowering the Parish Ranger After discussion on priority 1, the working party agreed to take the following actions: - Hedgehog Highways Project plan approved and in progress. - Parish Clerk has sent Enahncing Biodiversity Report to committee per request. Corridors not officially adopted as of yet, aside from accepting this action plan by full council. Full Council voted to have Ecologist who wrote the report do a presentation on nature recovery and conduct walks with full council to support nature recovery as part of upcoming neighbourhod plan refresh. · - · Engage the community through the newsletter and social media and Alwoodley 2030 groups to start to identify intervention sites. Action – SW & RH.- Progress update requested. |
| Provision & Maintenance of Community Facilities and Assets | Priority 1: to have an improved list of assets and clear directives from Council on desired future of each. | - Review contracts, sub-leases, and relationships with groups to identify risks and opportunities - Review asset register to ensure it is being kept according to proper practice and as a useful record. - Meet with ACA and other organisations with amenity space to explore how to work together with the Parish Council | - Clerk - Clerk - Clerk | - September 2026 - “ - “ | - Complete - Complete - Meeting with Cllrs Pritchard and Wright and ACA reps, and Clerk, 4th September clarified. |