## Proposal: Hedgehog Highways Project

## Aims

The Environment and Biodiversity Working Group Proposes a Hedgehog Highways project. The project aims to

- engage local people to protect hedgehogs – by providing shelter and safe passage, and will be rolled out in two phases.

- deepen a sense of neighbourliness collaboration as we’ll invite neighbours to work together.

- with local organisations and extend the reach of the Parish Council through this partnership.

## Plan

Phase I: Autumn – Shelter

| Task | Responsible Person | Deadline |
| --- | --- | --- |
| Create signup form to participate in project. Participating households can receive a hedgehog highway, native hedge/tree whips, and info on what hedgehogs need during autumn/winter. (Target 50 hedgehog houses/50 Trees). People can opt to receive either or both. | Clerk | September 15th |
| Create Poster to promote signups | Clerk | September 15th |
| Include piece in the PC newsletter to promote signups for the project | Clerk & Engagement committee | September 30th |
| Add a pop up to the website to promote signups | Clerk | September 30th |
| Host a “Show Us Your Hedgehog & Wildlife Photos” stall at the Brass Band Event Sept 26th and at POP Up Surgeries throughout October | TBD – Possibly Parish Councillors in conjunction with Volunteers from Alwoodley 2030 | Sept 26th at Event Possible additional dates. |
| Order Hedgehog houses and create/design print leaflets. Coordinate with Alwoodley 2030 to ensure trees are ordered. | Clerk+ EB Working Party | By end of Oct based on sign up list |
| Distribute hedgehog houses & Info leaflets | - Councillors to deliver hedgehog houses and use the opportunity to meet and chat with local people / or set up collection points - Clerk can have set collection hours at the PC - Alwoodley 2030 volunteers to deliver trees. | November 15th |

Spring – Safe Passage (Hedgehog Highways)

| Task | Responsible Person | Deadline |
| --- | --- | --- |
| New signup form to request hedgehog highway hole to be drilled by Ranger and / or install a hedgehog highway sign. Must have consent of neighbour. | Clerk | February 28th |
| Instal Hedgehog Crossing Signs (to be taken down in Autum/Winter). Will require permission from LCC to site placement and post. | Clerk and Ranger |  |
| Publicity on website, newsletter, at Councillor Surgeries | Clerk & Councillors | February 28th |
| Ranger to drill holes and install hedgehog highway signs (people can do this themselves or request ranger. | Ranger (for those who request) Councillors to deliver signs to those who wish to install themselves. | March 31st. |
| Groups of neighbours with the most sign-ups and interest will be rewarded with a hedgehog tracking tunnel (max 5). Installing these will also enable the Parish Council to establish baseline measurements and track increase in hedgehog activity year upon year. | EB Working Party in collaboration with keen resident point people. | March 31st |

## Budget

|  | 2026/2027 Budget | 2027/2028 Budget |  |
| --- | --- | --- | --- |
| Hedgehog houses (x20) | 540 |  | Link to Product |
| Hedgehog Crossing Signs (20) - Small |  | 250 | Link to Product |
| Hedgehog Highway hole signs (x 50) | 300 |  |  |
| Hedgehog Tracking Tunnel (x 5) |  | 79.75 | Link to Product |
| Ranger Installation Time | 950 |  |  |
| Promotional Posters | 30 | 30 |  |
|  | 1820 | 359.75 |  |